## TRADE SHOWS
BLUE CORP TRADE SHOW |  |  |  |  | ü
Planner Checklist
×
| In-Person |  | Virtual |  | ?
| Details |  | How will this change?
Pre-Planning
Determine Trade Show Revenue Goals with Stakeholders | ü | Look at previous years attendee numbers, growth, revenue generated. Identify growth rate, etc. For a new trade show; look at industry demand, prices, etc. | ü | Attrition numbers are more important to pay attention to as they might be larger. greater reach, what sort of new attendees will we see?
Kick off Meeting with Sales Org & Leaders | ü | Run through strategy, sales targets, etc. | ü | if you don't normally run these then this is a good chance to look at this in a virtual environment, possiblity the content may change and this will be needed to be considered in this kick-off
Sponsorship Prospectus | ü | Build out packages of sponsorships that are available (trade show booth, mobile app, etc.) | ü | Leverage mobile app usage using dyanmic event guide, create a platform for sponsors on registration website, include breaks with sponsor messaging throughout the day
Planning Logistics
Inventory Management once Sales closes "exhibitor" | ü | Keeping a pulse check on what spaces/sponsorships are still available as you gain more exhibitors | ü | faciliating the ability for 1:1 meetings, maybe making sure each exhibitors has some their own license for a virtual meetings
Floor Plan Design | ü | Map out how the tradeshow floor will look, where booths are placed, food/beverage stations, etc. | × | depends on the complexity of the event but if there are a lot of components this will need to be designed
Floor Plan Placement | ü | Where in the venue will the tradeshow live? | ü | Need a floor plan of the virtual environment and to consider where sponsors and exhibitors are placed in the virtual environment
Electrical/AV Coordination | ü | Negotiating AV contract | ü | Not physical AV but need to consider bandwidth, timing, production
Ad Hoc Furniture Requests for Premier Exhibitors | ü | Coordinating additional furniture requests from exhibitors | ×
Staffing Management | ü | Planning out staff roles and responsibilities and schedules | ü | Staffing with Exhibitors - could have exhibitors as breakout hosts Might not need as many front facing staff on the day but will need them to be avilable to answer questions online
Tech
Exhibitor Resource Center | ü | Build portal where exhubitors can access booth information, agenda, promotional took-kits, etc. | ü | Still important to share promotional tool-kit, information on how the event is set up, virtual agenda, training on how to use virtual platforms.
Cvent Appointments Tool | ü | Build out how exhibitors and attendees can network with eachother and schedule appointments. | ü | Getting each exhibitors on virtual platform to host meetings
Lead Capture | ü | Enable your exhibitors to track who they met with and follow up on new opportunities with LeadCapture. | ü | It's important to collect leads through exhibitor appointments. Maybe it's a form fill you can track for each exhibitor and an inbox they can send their information to?
Post Event Survey | ü | Build out exhibitor specific survey to collect feedback | ü | Can better target on a virtual event, can tailor to what sepcifically they went to and saw
Campaign
Work with Event Marketing for Key Milestons | ü | Outline promotional schedule: launch of sponsorship prospectus, email campaign to drive sponsorship sales | ü | Likely would send out more promotion pushes due to the changes/updates in agenda and content from in person event
Instructional Emails | ü | Emails to inform exhibitors of how to complete sposnorship documents, booth selection, booth set-up, adding booth staff, etc. | ü | Extremely important but will be more focused on the virtual platform training
Deliverable Followup Emails | ü | Emails to notify exhibitors of outstanding items they have not completed | ü | still needed - not much change in virtual environment
Appointment Scheduling Emails | ü | Instructional emails of how exhibitors can request/schedule appointments with attendees | ü | still needed - not much change in virtual environment
Pre-Event
Registrants and Appointments Report | ü | Check who has registered for the event via Cvent registration, pull report of how many appointments have been scheduled via Cvent Appointments tool | ü | still needed - how you pull appointment data will change which makes it important to have a structure and a way to track appointments/leads collected to show sponsorship ROI
Staff Pre-Con | ü | Train staff on FAQs, schedule, etc. | ü
Day-Of Execution
Appointment No Show Reports | ü | Check in on who did not show for any appointments, work with exhibitors on scheduling new appointments | ü | still needed - important to have a structure and a way to track appointments/leads collected to show sponsorship ROI
Send notifications through event mobile app or emails |  | to notify start and end of tradeshow hours |  | Can do this through virtual chat functionality or emails
Tech Desk for Trouble Shooting | ü | staffing tech/help desk to help exhibitors with questions on booth set-up, tech, furniture, schedule, etc. | ü | Tech desk/help desk will be virtual - maybe an open virtual room that people can join with breakout rooms that are specific to different needs
Post-Show
Leads Collected | ü | Pull reports from Cvent LeadCapture to see how exhibitors performed | ü | still needed - important to have a structure and a way to track appointments/leads collected to show sponsorship ROI
Post-Show Sales Tasks | ü | Get LeadCapture data to flow into marketing automation system to load follow up tasks for internal sales teams who collected leads | ü | still needed - important to have a structure and a way to track appointments/leads collected to show ROI for your organization
Staff Post-Con | ü | Recap of performance metrics (registrations, leads, etc.) | ü | still needed - not much change in virtual environment
Final Budget and ROI Analysis | ü | Budget vs Actual cost analysis | ü | The metrics for this may change depending on what information is being gathered for the virtual event